## TestStrategy
Project Name | Puggysoft
Test Strategy
Scope | * Who will review the test plan ? - PO, Technical Lead and Manager. * Who will review the test cases? - Team Technical Lead. * Who will approve the test plan ? - PO. * Who will approve the test cases? - Team Technical Lead.
Approach | * How will be the testing process ? * Analysis(Review Documents regarding feature,User Requirements) * Design (Create Test Plan) * Development (Create test cases) * Testing (Execute Test cases) * Open Bugs. * Send Reports * What testing levels we are going to test ? - Unit Test (Developers) - Integration Testing (Developers) - System Testing (QA) - Acceptance Testing (QA with PO)
Approach | * What are de Roles and Responsaibilities of each team member: - Juan (Team Lead) - Alvaro (Frontend Web QA) - Daniel (Backend Web QA) - Maria (Frontend and Backend QA) * What are the testing types that we are going to use ? - Load testing - Security testing - Performace testing. - Boundaries Testing. - BlackBox Testing. * What are the testing aproachs that we are going to use ? - Manual Testing. - Automation Testing. - Add Regression testing each week. - Add Acceptance Testing each week.
Test Environment | What are the requirement for each test environment ? - Android. - Iphone. - Sansung Galaxy S10. - Iphone 10. - Lector de codigo de barras. - Windows 10. What is the number of tests environments that we are going to use ? - 4 Sansung Galaxy S10. - 3 phone 10. - 2 Windows 10.
Testing Tools | What Testing Tools we are going to use ? - Manual: Jira, TestLodge. - Automation: Cucumber, Selenium. - Virtual machines for Andorid.
Risk Analysis | - What are the list of risks ? - Team Members Vacations. - Team Members Sicks. (Enfermedad) - Team Members renounce (Renuncia) - What is the contingency plan ?
Release Control | * Release Dates. * Versions that we are going to tests. * Builds that we are going to tests
Review and Approvals
Approach: Types | ### 1 Static Testing * Informal Reviews. * Walkthrought. * Technical Reviews. * Inspections. * Static Analysis. * Data flow. * Control flow. ### 2 Dinamic Testing * Functional Testing * Non-Functional Testing * Positive Testing * Negative Testing * Black Box Testing * White Box Testing * Gray Box Testing * Frontend Testing * Backend Testing * Databases Testing * Unit Testing * Integration Testing * Component Testing * System Testing * Acceptance Testing * Regression Testing